## Register
Stakeholder Register
Global Green Books Publishing - eBook Production Improvement Project
Instructions: Enter up to five stakeholders in cells B9-B13. Identify the Stakeholder's Name, Role or Title, and Type (Internal Customer/Internal Non-Customer/External Customer/External Non-Customer) Do not change any values in column A.
ID | Stakeholder | Role/Title | Stakeholder Type
A | Owners of Global Green books | Owner | Internal
B | Samantha | PM Assistant | Internal
C | Part-Time Employees | Printing associate | Internal Customer
D | Local College | Client | External
E | Professors | Middleman | External

## Grid 1
Stakeholder Power/Interest Grid
Global Green Books Publishing - eBook Production Improvement Project
Instructions: Update the Interest and Power values according to the following scale: 1 = no power or interest 2 = low power or interest 3 = moderate power or interest 4 = high power or interest 5 = extremely high power or interest Stakeholder Names were pulled forward from the Register tab. Do not change any values in column A or B. The chart will self update.
ID | Stakeholder | Power | Interest
A | Owners of Global Green books | 5 | 5
B | Samantha | 4 | 5
C | Part-Time Employees | 2 | 3
D | Local College | 1 | 4
E | Professors | 1 | 4
Low High
Low High

## Grid 2
Stakeholder Expectations/Importance to Success Grid
Global Green Books Publishing - eBook Production Improvement Project
Instructions: 1. Add one expectation that each stakeholder holds regarding the project (an expectation about what is delivered, how it is delivered, who delivers it, etc). 2. Indicate if the expectation will have a positive or negative impact on the project's success. Also indicate the significance (importance) of the impact (High/Low). Do not change any values in column A or B. Note that one chart is a bubble chart that shows the number of expectations by Expectation/Importance and the other shows individual records. Where multiple expectations have the same rating, one may overlay another and make it appear that the record is not shown. The charts will self update.
ID | Stakeholder | Expectation | Positive/Negative | Significance (Importance) | PN Convert | Sig Convert
A | Owners of Global Green books | Profit | Positive | High | 1 | 1
B | Samantha | Project Success | Positive | High | 1 | 1
C | Part-Time Employees | Work and pay | Negative | Low | -1 | -1
D | Local College | Quality Product received | Negative | High | -1 | 1
E | Professors | Quality Product received | Negative | Low | -1 | -1
[7 empty] | Positive/Negative | Significance (Importance) | Count
[7 empty] | 1 | 1 | 2
[7 empty] | 1 | -1 | 0
[7 empty] | -1 | 1 | 1
[7 empty] | -1 | -1 | 2

## Mgt Plan
Stakeholder Management Plan
Global Green Books Publishing - eBook Production Improvement Project
Instructions: 1. Choose one of the stakeholders and based on your analysis thus far. In the respective row, document an action plan to manage their power/interest and expectations/importance to achieve a successful project outcome in column J. Do not change any values in column A through I.
ID | Stakeholder | Role/Title | Stakeholder Type | Interest | Power | Expectation | Positive/Negative | Significance (Importance) | Action Plan
A | Owners of Global Green books | Owner | Internal | 5 | 5 | Profit | Positive | High
B | Samantha | PM Assistant | Internal | 4 | 5 | Project Success | Positive | High | Implement PM plan, PM software, and training plan
C | Part-Time Employees | Printing associate | Internal Customer | 2 | 3 | Work and pay | Negative | Low
D | Local College | Client | External | 1 | 4 | Quality Product received | Negative | High
E | Professors | Middleman | External | 1 | 4 | Quality Product received | Negative | Low

## EXAMPLE Register
Stakeholder Register
Disney World Renovations
Instructions: Enter up to five stakeholders in cells B9-B13. Identify the Stakeholder's Name, Role or Title, and Type (Internal Customer/Internal Non-Customer/External Customer/External Non-Customer) Do not change any values in column A.
ID | Stakeholder | Role/Title | Stakeholder Type
A | Mickey | Sponsor | Internal
B | Minnie | Finance Director | Internal Customer
C | Donald | Engineer | Internal Customer
D | Goofy | Entertainer | External
E | Pluto | Pet | Internal

## EXAMPLE Grid 1
Stakeholder Power/Interest Grid
Disney World Renovations
Instructions: Update the Interest and Power values according to the following scale: 1 = no power or interest 2 = low power or interest 3 = moderate power or interest 4 = high power or interest 5 = extremely high power or interest Do not change any values in column A or B. The chart will self update.
ID | Stakeholder | Power | Interest
A | Mickey | 3 | 5
B | Minnie | 2 | 4
C | Donald | 4 | 3
D | Goofy | 1 | 3
E | Pluto | 1 | 1
Low High
Low High

## EXAMPLE Grid 2
Stakeholder Expectations/Importance to Success Grid
Disney World Renovations
Instructions: 1. Add one expectation that each stakeholder holds regarding the project (this could be an expectation about what is delivered, how it is delivered, who delivers it, etc). 2. Indicate if the expectation will have a positive or negative impact on the project's success. Also indicate the significance (importance) of the impact (High/Low). Do not change any values in column A or B. Note that one chart is a bubble chart that shows the number of expectations by Expectation/Importance and the other shows individual records. Where multiple expectations have the same rating, one may overlay another and make it appear that the record is not shown. The charts will self update.
ID | Stakeholder | Expectation | Positive/Negative | Significance (Importance) | PN Convert | Sig Convert
A | Mickey | Use PMBOK | Positive | High | 1 | 1
B | Minnie | Reduce costs | Negative | High | -1 | 1
C | Donald | Stabilize castle | Positive | High | 1 | 1
D | Goofy | More guests | Positive | Low | 1 | -1
E | Pluto | Get a treat | Positive | Low | 1 | -1
[7 empty] | Positive/Negative | Significance (Importance) | Count
[7 empty] | 1 | 1 | 2
[7 empty] | 1 | -1 | 2
[7 empty] | -1 | 1 | 1
[7 empty] | -1 | -1 | 0

## EXAMPLE Mgt Plan
Stakeholder Management Plan
Disney World Renovations
Instructions: 1. Choose one of the stakeholders and based on your analysis thus far, document an action plan to manage their power/interest and expectations/importance to achieve a successful project outcome. Do not change any values in column A through I.
ID | Stakeholder | Role/Title | Stakeholder Type | Interest | Power | Expectation | Positive/Negative | Significance (Importance) | Action Plan
A | Mickey | Sponsor | Internal | 3 | 5 | Use PMBOK | Positive | High
B | Minnie | Finance Director | Internal Customer | 2 | 4 | Reduce costs | Negative | High | Communicate actual spend frequently to allay concerns
C | Donald | Engineer | Internal Customer | 4 | 3 | Stabilize castle | Positive | High
D | Goofy | Entertainer | External | 1 | 3 | More guests | Positive | Low
E | Pluto | Pet | Internal | 1 | 1 | Get a treat | Positive | Low