## Sheet
Level | Code | Task
1 | Office | Move
2 | Office.1. | Manage Project
3 | Office.1..1.1 | Define Requirements
4 | Office.1..1.1.1.1.1 | Identify Stakeholders
4 | Office.1..1.1.1.1.2 | Conduct Needs Assessment
4 | Office.1..1.1.1.1.3 | Document Business Requirements
3 | Office.1..1.1.1.2 | Set Budget
4 | Office.1..1.1.1.2.1.2.1 | Estimate Moving Costs
4 | Office.1..1.1.1.2.1.2.2 | Estimate New Office Setup Costs
4 | Office.1..1.1.1.2.1.2.3 | Finalize Budget Approval
4 | Office.1..1.1.1.2.1.2.4 | Create Budget Timeline
5 | Office.1..1.1.1.2.1.2.4.1.2.4.1 | Schedule Money Transfers
5 | Office.1..1.1.1.2.1.2.4.1.2.4.2 | Align Transfers with Activity Start Dates
5 | Office.1..1.1.1.2.1.2.4.1.2.4.3 | Monitor Cash Flow to Avoid Delays
3 | Office.1..1.1.1.3 | Create Schedule
4 | Office.1..1.1.1.3.1.3.1 | Develop Project Timeline
4 | Office.1..1.1.1.3.1.3.2 | Assign Responsibilities
4 | Office.1..1.1.1.3.1.3.3 | Set Key Milestones
3 | Office.1..1.1.1.4 | Risk Management & Compliance
4 | Office.1..1.1.1.4.1.4.1 | Identify Potential Risks
4 | Office.1..1.1.1.4.1.4.2 | Develop Contingency Plan
4 | Office.1..1.1.1.4.1.4.3 | Ensure Legal & Compliance Review
2 | Office.1..2. | New Office
3 | Office.1..2..2.1 | Realtor
4 | Office.1..2..2.1.2.1.1 | Research Available Locations
4 | Office.1..2..2.1.2.1.2 | Schedule Site Visits
4 | Office.1..2..2.1.2.1.3 | Compare Lease Agreements
4 | Office.1..2..2.1.2.1.4 | Compare Lease Costs
3 | Office.1..2..2.2 | Identify Location
4 | Office.1..2..2.2.2.2.1 | Evaluate Accessibility for Customers and Employees
4 | Office.1..2..2.2.2.2.2 | Assess Space Requirements
4 | Office.1..2..2.2.2.2.3 | Check Zoning & Permits
3 | Office.1..2..2.3 | Sign Lease
4 | Office.1..2..2.3.2.3.1 | Negotiate Lease Terms
4 | Office.1..2..2.3.2.3.2 | Conduct Legal Review
4 | Office.1..2..2.3.2.3.3 | Finalize Lease Agreement
2 | Office.1..3. | Equipment & Furniture
3 | Office.1..3..3.1 | Select Suppliers
4 | Office.1..3..3.1.3.1.1 | Research & Compare Vendors
4 | Office.1..3..3.1.3.1.2 | Obtain Quotes & Approvals
4 | Office.1..3..3.1.3.1.3 | Place Orders
3 | Office.1..3..3.2 | Furniture Selection
4 | Office.1..3..3.2.3.2.1 | Identify Office Layout Needs
4 | Office.1..3..3.2.3.2.2 | Choose Ergonomic Seating
4 | Office.1..3..3.2.3.2.3 | Order Assembly & Installation
3 | Office.1..3..3.3 | Computer Equipment Selection
4 | Office.1..3..3.3.3.3.1 | Decide on Computers & Monitors (Transfered or new)
4 | Office.1..3..3.3.3.3.2 | Procure Printers & Networking Devices (Transfered or new)
4 | Office.1..3..3.3.3.3.3 | Set Up Server & Cloud Services
2 | Office.1..4. | Move
3 | Office.1..4..4.1 | Packing Plan
4 | Office.1..4..4.1.4.1.1 | Develop Packing Guidelines
4 | Office.1..4..4.1.4.1.2 | Label & Inventory Items
4 | Office.1..4..4.1.4.1.3 | Organize Packing Teams
3 | Office.1..4..4.2 | Select Moving Company
4 | Office.1..4..4.2.4.2.1 | Obtain Quotes
4 | Office.1..4..4.2.4.2.2 | Schedule Move Date
4 | Office.1..4..4.2.4.2.3 | Coordinate Logistics
3 | Office.1..4..4.3 | Transportation & Setup
4 | Office.1..4..4.3.4.3.1 | Plan Delivery Routes
4 | Office.1..4..4.3.4.3.2 | Oversee Equipment Unloading
4 | Office.1..4..4.3.4.3.3 | Ensure Proper Setup
3 | Office.1..4..4.4 | Post-Move Activities
4 | Office.1..4..4.4.4.4.1 | Conduct Final Walkthrough
4 | Office.1..4..4.4.4.4.2 | Resolve Any Issues
4 | Office.1..4..4.4.4.4.3 | Collect Feedback & Adjustments